## ROM Calculator
ROM Calculator
Delivery Risk-Adjusted Rough Order of Magnitude — v1.0
ENGAGEMENT TYPE |  |  | ← Select from dropdown
Type | Implementation
Engagement Modifier | 1 |  | Auto-calculated based on type
BASE ESTIMATE
Base Effort (Hours) | 1000 |  | ← Your initial estimate
Blended Rate ($/hr) | 175
Naive Estimate | 175000
RISK FACTORS |  |  | Enter from Diagnostic worksheet
Factor | Multiplier | Cumulative | Range
1. Competence | 1 | 1 | 1.0 → 1.2
2. Architectural Debt | 1 | 1 | 1.0 → 1.4
3. Legacy Systems | 1 | 1 | 1.0 → 1.2
4. Bend Resistance | 1 | 1 | 1.0 → 1.15
5. Machine Readiness | 1 | 1 | 1.0 → 1.15
6. Governance Friction | 1 | 1 | 1.0 → 1.15
7. Integration Complexity | 1 | 1 | 1.0 → 1.15
8. Platform Maturity | 1 | 1 | 1.0 → 1.1
9. Customer Readiness | 1 | 1 | 1.0 → 1.2
10. Data Foundations | 1 | 1 | 1.0 → 1.2
11. CSDM/CMDB Maturity | 1 | 1 | 1.0 → 1.3
RESULTS
Base Risk Multiplier | 1
TOTAL RISK MULTIPLIER | 1 |  | Base × Engagement Modifier
Adjusted Hours | 1000
REALITY-ADJUSTED ROM | 175000
Risk Delta | 0 |  | What optimism costs you
Percent Increase | 0%
FIVE TAXES VIEW |  |  | Conceptual mapping to book framework
Competence Tax | 1 |  | Factor 1
Architectural Debt Tax | 1 |  | F2 × F11
Legacy Tax | 1 |  | Factor 3
Bend Tax | 1 |  | Factor 4
Machine's Tax | 1 |  | F5 × F8
Operational Factors | 1 |  | F6 × F7 × F9 × F10
RISK ASSESSMENT
Risk Level | LOW
Field Move | Proceed with standard 10-15% contingency.
© SYTYCSN Institute ¦ www.sytycsn.com

## Instructions
ROM Calculator Instructions — v1.0
═══════════════════════════════════════════════════════════════════════════════════
💡 Use the Delivery Risk Diagnostic (PDF) from www.sytycsn.com
to assess each factor before entering values here.
═══════════════════════════════════════════════════════════════════════════════════
HOW TO USE THIS CALCULATOR
1. SELECT ENGAGEMENT TYPE
Choose from the dropdown: Assessment, Implementation, Rescue/Remediation, Upgrade, or Optimization
This automatically adjusts the engagement modifier.
2. ENTER BASE ESTIMATE
Hours: Your initial 'gut feel' or vendor-provided estimate
Rate: Your blended hourly rate (internal + external resources)
3. COMPLETE THE DIAGNOSTIC
Download the Delivery Risk Diagnostic PDF from www.sytycsn.com
Work through all 11 factors and determine your multipliers
4. ENTER FACTOR MULTIPLIERS
Transfer your multipliers from the diagnostic into the calculator
Each factor compounds with the others
5. REVIEW RESULTS
- Total Risk Multiplier: Your overall delivery risk factor
- Reality-Adjusted ROM: What you should actually budget
- Risk Delta: The cost of optimism
- Five Taxes View: Conceptual breakdown aligned with book framework
───────────────────────────────────────────────────────────────────────────────────
THE 11 RISK FACTORS
1. COMPETENCE (1.0 → 1.2×) → Competence Tax
Team skill gaps, learning curves, expertise mismatches
2. ARCHITECTURAL DEBT (1.0 → 1.4×) → Architectural Debt Tax
Tech debt, customization sins, upgrade backlog, data quality
3. LEGACY SYSTEMS (1.0 → 1.2×) → Legacy Tax
Dual environments, sunset resistance, competing sources of truth
4. BEND RESISTANCE (1.0 → 1.15×) → Bend Tax
Forcing platform to match legacy processes
5. MACHINE READINESS (1.0 → 1.15×) → Machine's Tax
AI/automation foundation quality, data governance
6. GOVERNANCE FRICTION (1.0 → 1.15×) → Operational
CAB delays, approval chains, compliance overhead
7. INTEGRATION COMPLEXITY (1.0 → 1.15×) → Operational
API complexity, data migration, connectivity
8. PLATFORM MATURITY (1.0 → 1.1×) → Machine's Tax
Version currency, licensing gaps, multi-instance
9. CUSTOMER READINESS (1.0 → 1.2×) → Operational
Sponsor engagement, SME availability, decision authority
10. DATA FOUNDATIONS (1.0 → 1.2×) → Operational
Core table quality: users, groups, locations, companies
11. CSDM/CMDB MATURITY (1.0 → 1.3×) → Architectural Debt Tax
Configuration management foundation, CI ownership, Service Mapping
Note: Set to 1.0× if not implementing CMDB-dependent modules
───────────────────────────────────────────────────────────────────────────────────
ENGAGEMENT TYPE MODIFIERS
Assessment: 0.70× — Discovery/analysis only, no build
Implementation: 1.00× — Standard delivery (baseline)
Rescue/Remediation: 1.15× — Recovery from prior failure
Upgrade: 1.05× — Version migration focus
Optimization: 1.05× — AI/automation enablement focus
───────────────────────────────────────────────────────────────────────────────────
INTERPRETING RESULTS
1.0× – 1.5× LOW Proceed with standard contingency (10-15%)
1.5× – 2.0× MODERATE Add buffer, increase oversight
2.0× – 2.5× HIGH Revisit scope, phase work, executive alignment
2.5× + CRITICAL STOP — Reframe scope or pivot to remediation
───────────────────────────────────────────────────────────────────────────────────
FIVE TAXES VIEW
The calculator shows how your 11 factors map to the Five Taxes framework:
• Competence Tax = Factor 1
• Architectural Debt = Factor 2 × Factor 11
• Legacy Tax = Factor 3
• Bend Tax = Factor 4
• Machine's Tax = Factor 5 × Factor 8
• Operational = Factor 6 × Factor 7 × Factor 9 × Factor 10
This connects the practical diagnostic to the conceptual framework
explained in 'So You Think You Can ServiceNow' Book 2.
───────────────────────────────────────────────────────────────────────────────────
© SYTYCSN Institute ¦ From 'So You Think You Can ServiceNow'
Most ROMs hide risk. This one exposes it.